## Template - 3-Year Project
Knowledge Management Implementation Timeline | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
Date:
Developed by: | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept
Version #:
1. ASSESS NEEDS | bar: Oct; Oct to Sept
1. Identify the health problem that KM can help solve.
2. Define the audience of your needs assessment.
3. Decide on key questions you want the needs assessment to answer.
4. Select and implement the appropriate methods to answer your key questions.
5. Analyze and synthesize the needs assessment findings.
2. DESIGN STRATEGY | bar: Oct
1. Decide on KM objectives.
2. Define your audiences.
3. Ground the KM intervention with a relevant theoretical framework.
4. Decide on KM tools and techniques and appropriate ICTs.
5. Develop a budget and an implementation plan.
6. Develop a monitoring and evaluation plan.
7. Bring together relevant stakeholders to launch the KM intervention.
3. CREATE AND ITERATE | bar: Oct
1. Identify your KM team.
2. Draft the KM tools and techniques.
3. Test or gather feedback about the KM tools and techniques, revise, and retest.
4. Finalize the KM tools and techniques.
4. MOBILIZE AND MONITOR | bar: Oct
1. Implement your KM intervention and keep the team updated.
2. Review progress toward KM objectives.
3. Adapt as necessary.
5. EVALUATE AND EVOLVE | bar: Oct
1. Decide which program outcomes to measure.
2. Choose the evaluation design.
3. Collect, analyze, and synthesize the evaluation data.
4. Share evaluation findings with key stakeholders.
5. Promote use of evaluation findings in policy and practice.
*Work plan and timeline will be revised upon completion of needs assessment.

## Sample - 3-Year Project
Knowledge Management Implementation Timeline | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
Date:
Developed by: | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept
Version #:
1. ASSESS NEEDS | bar: Oct; Oct to Sept
1. Identify the health problem that KM can help solve. | bar: Oct
2. Define the audience of your needs assessment. | bar: Oct to Nov
3. Decide on key questions you want the needs assessment to answer. | bar: Oct to Dec
4. Select and implement the appropriate methods to answer your key questions. | bar: Nov to Dec
5. Analyze and synthesize the needs assessment findings. | bar: Dec to Jan
2. DESIGN STRATEGY | bar: Oct
1. Decide on KM objectives. | bar: Jan
2. Define your audiences. | bar: Jan
3. Ground the KM intervention with a relevant theoretical framework. | bar: Jan
4. Decide on KM tools and techniques and appropriate ICTs. | bar: Jan
5. Develop a budget and an implementation plan. | bar: Jan
6. Develop a monitoring and evaluation plan. | bar: Jan to Feb
7. Bring together relevant stakeholders to launch the KM intervention. | bar: Jan to Feb
3. CREATE AND ITERATE | bar: Oct
1. Identify team to create outputs | bar: Jan to Mar
2. Draft the KM tools and techniques. | bar: Mar to Jun; Dec to Jan; Dec to Jan
3. Test or gather feedback about the KM tools and techniques, revise, and retest. | bar: Apr to Jun; Mar to Apr; Mar to Apr
4. Finalize the KM tools and techniques. | bar: Jun to Sep; Apr to Sept; Apr to Sept
4. MOBILIZE AND MONITOR | bar: Oct
1. Implement your KM intervention and keep the team updated. | bar: Oct to Sept
2. Review progress toward KM objectives. | bar: Feb; Jun; Sep; Dec; Mar; Jun; Sept; Dec; Mar; Jun; Sept
3. Adapt as necessary. | bar: Feb to Mar; Jun; Sep; Dec; Mar; Jun; Sept; Dec; Mar; Jun; Sept
5. EVALUATE AND EVOLVE | bar: Oct
1. Decide which program outcomes to measure. | bar: Oct to Dec
2. Choose the evaluation design. | bar: Feb to Apr
3. Collect, analyze, and synthesize the evaluation data. | bar: Mar to May; May to Jun
4. Share evaluation findings with key stakeholders. | bar: Jun to Aug; Jul to Sept
5. Promote use of evaluation findings in policy and practice. | bar: Aug to Sept; Aug to Sept
*Work plan and timeline will be revised upon completion of needs assessment.

## Template - 3-Month Project
Knowledge Management Implementation Timeline | Month 1 |  |  |  | Month 2 |  |  |  | Month 3
Date:
Developed by: | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
Version #: | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. ASSESS NEEDS
1. Identify the health problem that KM can help solve.
2. Define the audience of your needs assessment.
3. Decide on key questions you want the needs assessment to answer.
4. Select and implement the appropriate methods to answer your key questions.
5. Analyze and synthesize the needs assessment findings.
2. DESIGN STRATEGY
1. Decide on KM objectives.
2. Define your audiences.
3. Ground the KM intervention with a relevant theoretical framework.
4. Decide on KM tools and techniques and appropriate ICTs.
5. Develop a budget and an implementation plan.
6. Develop a monitoring and evaluation plan.
7. Bring together relevant stakeholders to launch the KM intervention.
3. CREATE AND ITERATE
1. Identify team to create outputs.
2. Draft the KM tools and techniques.
3. Test or gather feedback about the KM tools and techniques, revise, and retest.
4. Finalize the KM tools and techniques.
4. MOBILIZE AND MONITOR
1. Implement your KM intervention and keep the team updated.
2. Review progress toward KM objectives.
3. Adapt as necessary.
5. EVALUATE AND EVOLVE
1. Decide which program outcomes to measure.
2. Choose the evaluation design.
3. Collect, analyze, and synthesize the evaluation data.
4. Share evaluation findings with key stakeholders.
5. Promote use of evaluation findings in policy and practice.

## Sample - 3-Month Project
Knowledge Management Implementation Timeline | Month 1 |  |  |  | Month 2 |  |  |  | Month 3
Date:
Developed by: | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
Version #: | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. ASSESS NEEDS
1. Identify the health problem that KM can help solve. | x
2. Define the audience of your needs assessment. | x
3. Decide on key questions you want the needs assessment to answer. | x | x
4. Select and implement the appropriate methods to answer your key questions. | x | x
5. Analyze and synthesize the needs assessment findings. |  | x
2. DESIGN STRATEGY
1. Decide on KM objectives. |  | x
2. Define your audiences. |  | x
3. Ground the KM intervention with a relevant theoretical framework. |  | x
4. Decide on KM tools and techniques and appropriate ICTs. |  |  | x
5. Develop a budget and an implementation plan. |  |  | x
6. Develop a monitoring and evaluation plan. |  |  | x
7. Bring together relevant stakeholders to launch the KM intervention. |  |  | x
3. CREATE AND ITERATE
1. Identify team to create outputs |  |  | x
2. Draft the KM tools and techniques. |  |  |  | x | x
3. Test or gather feedback about the KM tools and techniques, revise, and retest. | [5 empty] | x
4. Finalize the KM tools and techniques. | [5 empty] | x
4. MOBILIZE AND MONITOR
1. Implement your KM intervention and keep the team updated. | [5 empty] | x | x | x | x
2. Review progress toward KM objectives. | [5 empty] | x | x | x | x
3. Adapt as necessary. | [7 empty] | x | x | x
5. EVALUATE AND EVOLVE
1. Decide which program outcomes to measure. | [8 empty] | x | x
2. Choose the evaluation design. | [10 empty] | x
3. Collect, analyze, and synthesize the evaluation data. | [10 empty] | x
4. Share evaluation findings with key stakeholders. | [11 empty] | x
5. Promote use of evaluation findings in policy and practice. | [11 empty] | x